## my_diary_notes
Id | User Id | Tags | Note Date | Content | Created At | Updated At
1dbe6b2e-e2f0-480f-9459-b4ce4347770a | 5fe01672-b062-4789-b809-8b30fc77c834 |  | 2025-10-29 | Attenteded SBI Baruipur Bazar fault, LC Id- 1000122714.Local mac was not being received. Checked the optical fibers and found them OK. There was an optical power loss in the media. The power loss was due to a fault in the HUAWEI port — the Tx power at the port itself was -17 dBm. Changing the SFP did not resolve the issue. Configuration was done in Tejas and the details were posted in the CPAN group for shifting to another CPAN port. After the CPAN configuration was completed by the CPAN team, MAC was received from both ends, and the media appeared to be OK. However, ping was still not successful from their router. The media converter and power adaptor at SBI Baruipur Bazar Branch were also replaced with a new one. The vendor was approached to check the issue at their local end. | 2025-10-27 | 2025-10-27
1dc875bb-f2fa-4706-8207-e3e2d68f59a8 | 5fe01672-b062-4789-b809-8b30fc77c834 |  | 2025-10-30 | SBI Baruipur Bazar fault, LC Id- 1000122714, attended by BSNL team and SBI vendor(8017384766) also. Got mac from both side. Ping from directly connected laptop was successful but through router, ping not successful. Suspected Tejas equipment card issue, so directly connected through CPAN and router ping also successful after that. Circuit restored. | 2025-10-29 | 2025-10-29
7a441cdc-cf56-465a-8eee-e15f7c569db0 | 5fe01672-b062-4789-b809-8b30fc77c834 |  | 2025-11-25 | LC ID- 1000123043 , SBI Subhasgram fault docket assigned. Found OFC cut at a distance of 3 km from Kamalgazi.There are 5 cable cuts at that location, 2 48F and 3 24F OFCs.SBI ckt restored diverting it. LMG shifted from MNGPAN(5.7) to GPON OLT Port-1. For diversion of BTS:- Sonarpur(VLAN-1748/1948), Sonarpur Teghoria(1006/1506), Narendrapur Krishna(1741/1941), Narendrapur II(1740/1940), Hindustan More(1489/1889), Sonarpur Kurigachi(1737/1937), Mandalpara(1071/1571), Boral II(1768/1968), Baruipur Kalyanpur(1792/1992), Barendrapara(1102/1602) written on CPAN group. Harinavi team alongwith SLA vendor attended the ofc cut site to restore that. | 2025-11-25 10:18 | 2025-11-25 10:18