## rings
Id | Name | Total Nodes | Description | Ring Type Id | Maintenance Terminal Id | Bts Status | Ofc Status | Spec Status | Is Closed Loop | Topology Config | Status | Created At | Updated At
73ec01ed-474a-44d1-8614-d2deaff6375a | ADM16/R-128 | 5 |  | cc3cebe7-5419-4806-8d3a-6405cf00ecbb | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
96bb958d-22bf-41b3-ba66-e5cb6fd12644 | ADM16/R-131 | 4 |  | cc3cebe7-5419-4806-8d3a-6405cf00ecbb | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
d370d0f5-b147-4417-b32a-92ebf711f4f7 | ADM16/R-135 | 3 |  | cc3cebe7-5419-4806-8d3a-6405cf00ecbb | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
f2d12fde-7958-4a5f-91e8-6a7a8d9b89ce | ADM16/R-136 | 6 |  | cc3cebe7-5419-4806-8d3a-6405cf00ecbb | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
db39d5c1-936b-476b-94df-f120aedb18fe | ADM16/R-137 | 6 |  | cc3cebe7-5419-4806-8d3a-6405cf00ecbb | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
2b85991d-8610-490b-907a-8c49029b343b | HNV_CPAN | 0 |  | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  |  | true | 2025-10-17 | 2025-12-07 14:48
d95f0c5e-10b5-4657-a6b2-2b894c6c5b08 | HNV-01 | 6 | <strong class="text-blue-600">OFC STATUS:</strong> OFC NOT READY FROM MAHI TO GDP.CPAN OFC CAN BE USED<br /> <strong class="text-green-600">SPEC STATUS:</strong> ISSUED Vide: TP/Inst. Prg/10_25/02 DATED: 06-10-2025<br /> <strong class="text-green-600">BTS STATUS:</strong> ON AIR<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | On-Air | Partial Ready | Issued |  |  | true | 2025-08-11 | 2025-12-07 14:48
d8836bb7-2f9c-484f-89ef-6d5cd6f4f51c | HNV-02 | 5 | <strong class="text-blue-600">OFC STATUS:</strong> READY<br /> <strong class="text-green-600">SPEC STATUS:</strong> ISSUED Vide: TP/Inst. Prg/11_25/30 DATED: 22-11-2025<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Configured | Ready | Issued |  |  | true | 2025-08-11 | 2025-12-07 14:48
17520ee6-a471-47ed-82c1-0590f4c4bad6 | HNV-03 | 4 | <strong class="text-green-600">OFC STATUS:</strong> READY WITH CPAN FIBRE<br /> <strong class="text-red-600">SPEC STATUS:</strong> Not Issued<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  | {"disabled_segments":["286ec15e-6eee-488e-9fd8-16b7fb859853-6200287c-2244-4b89-ba91-932301dbcfd7"]} | true | 2025-08-11 | 2025-12-07 14:48
08f32227-efbc-41d8-8171-363bf82b21ad | HNV-04 | 4 | <strong class="text-blue-600">OFC STATUS:</strong> READY<br /> <strong class="text-red-600">SPEC STATUS:</strong> Not issued<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
a36dd652-8850-4872-93f0-339e8d907754 | HNV-05 | 4 | <strong class="text-blue-600">OFC STATUS:</strong> READY<br /> <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  | {"disabled_segments":["3019cb42-9dca-4eaf-a349-2e4c0fae92e2-b5bfbef5-356c-499b-ad2b-351b7ed6a845","3019cb42-9dca-4eaf-a349-2e4c0fae92e2-45b41c2d-54cf-42a9-b134-239d96bb7c5a"]} | true | 2025-08-11 | 2025-12-07 14:48
6d920c57-cfda-48b3-842c-5598acc0f55c | HNV-06 | 4 | <strong class="text-green-600">OFC STATUS:</strong> READY<br /> <strong class="text-green-600">SPEC STATUS:</strong> ISSUED Vide: TP/Inst. Prg/02_25/21 DATED: 26-02-2025<br /> <strong class="text-green-600">RING STATUS:</strong> ON AIR<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | On-Air | Ready | Issued |  |  | true | 2025-08-11 | 2025-12-07 14:48
ea5a641a-0f55-40ad-bd7d-085aa2192c05 | HNV-07 | 4 | <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> <strong class="text-green-600">OFC STATUS:</strong> READY WITH CPAN FIBER<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Partial Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
c3415dbb-82fc-4c57-bbc7-030774d70494 | HNV-08 | 6 | <strong class="text-blue-600">OFC STATUS:</strong> READY WITH CPAN FIBRE | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Partial Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
d60d5adb-08af-47f6-a7c5-2c1daabed492 | HNV-09 | 3 | <strong class="text-green-600">SPEC STATUS:</strong> ISSUED Vide: TP/Inst. Prg/02_25/22_Revised DATED: 17-09-2025<br /> <strong class="text-green-600">BTS STATUS:</strong> ON AIR<br /> <strong class="text-amber-600">NOT INCLUDED IN SPEC:</strong> Dakshin Bonhoogly<br /> <strong class="text-blue-600">OFC STATUS:</strong> BOTH PRANA BORAL AND D BONHOOGLY BTS ON AIR FROM BORAL MAAN,OFC JOB PENDING BTN DAKSHIN BONHOOGLY AND BORAL MAAN<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | On-Air | Ready | Issued |  |  | true | 2025-08-11 | 2025-12-07 14:48
fb724801-3a0a-40fe-9bda-d34a8780a984 | HNV-10 | 6 | <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> <strong class="text-green-600">OFC STATUS:</strong> OFC READY WITH CPAN FIBRE<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Partial Ready | Pending |  |  | true | 2025-08-11 | 2025-12-11 11:40
87442c8d-1a10-46d4-ace6-fde25f87f7b8 | HNV-11 | 4 | <strong class="text-blue-600">OFC STATUS:</strong> READY<br /> <strong class="text-green-600">SPEC STATUS:</strong> ISSUED Vide: TP/Inst. Prg/08_25/01 DATED: 01-08-2025<br /> <strong class="text-green-600">RING STATUS:</strong> ON AIR<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | On-Air | Ready | Issued |  |  | true | 2025-08-11 | 2025-12-07 14:48
654e4085-294d-4b04-989f-b51905f33e41 | HNV-12 | 6 | <strong class="text-green-600">OFC STATUS:</strong> READY<br /> <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
b4351719-d26e-4b77-81df-8e359bb50504 | HNV-13 | 3 | <strong class="text-blue-600">OFC STATUS:</strong> READY<br /> <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
6a24ce8a-a80f-41bb-ab94-17159c33db08 | HNV-14 | 4 | <strong class="text-blue-600">OFC STATUS:</strong> READY<br /> <strong class="text-green-600">SPEC STATUS:</strong> ISSUED Vide: TP/Inst. Prg/11_25/29 DATED: 22-11-2025<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Configured | Ready | Issued |  |  | true | 2025-08-11 | 2025-12-07 14:48
e996fc48-1f78-4ca3-a2ba-ed1f3afa8755 | HNV-15 | 6 | <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> <strong class="text-blue-600">OFC STATUS:</strong> OFC READY UPTO NDP-II, DPR JOB PENDING,NEED OFC JOINT FOR FURTHER BTS ON ROUTE.<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
4c1e57c0-b9fc-4279-9ce9-30f943b905d2 | HNV-16 | 5 | <strong class="text-blue-600">OFC STATUS:</strong> HHC DPR JOB NOT YET DONE<br /> <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  | {"disabled_segments":[]} | true | 2025-08-11 | 2025-12-07 14:48
b2f50b65-79a6-4ef9-91a9-281253381db0 | HNV-17 | 3 | <strong class="text-blue-600">OFC STATUS:</strong> READY<br /> <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
09136fb5-6392-44bb-bab4-de1c22a2ac43 | HNV-18 | 2 | <strong class="text-green-600">OFC STATUS:</strong> READY<br /> <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
d1fd3f87-3f00-472f-9c09-b27c592fcde3 | HNV-19 | 2 | <strong class="text-green-600">OFC STATUS:</strong> READY<br /> <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
d754eb42-3981-4173-9d9d-3d98af98cfdd | HNV-20 | 4 | <strong class="text-blue-600">OFC STATUS:</strong> READY BUT NEED TO BE CHECKED<br /> <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
1e437e94-08ee-4e1d-9746-3f8aa136135c | HNV-21 | 3 | <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> <strong class="text-blue-600">OFC STATUS:</strong> READY WITH CPAN FIBER<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Partial Ready | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
44beae27-c244-4de8-8121-7f8995c3ce49 | HNV-22 | 8 | <strong class="text-green-600">OFC STATUS:</strong> Co-Located<br /> <strong class="text-green-600">SPEC STATUS:</strong> ISSUED Vide: TP/Inst. Prg/10_25/17 DATED: 17-10-2025<br /> <strong class="text-green-600">BTS STATUS:</strong> ON AIR<br /> <strong class="text-amber-600">LEFT OUT NODES IN SPEC:</strong> Mahamayatala II, GARIA KANDARPUR SAHAPARA, Narendrapur Station<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | On-Air | Ready | Issued |  |  | true | 2025-08-11 | 2025-12-07 14:48
9cc133bd-d206-4fc4-b0d8-5fb7cdd1e5c2 | HNV-23 | 5 | <strong class="text-green-600">OFC STATUS:</strong> CO-LOCATED<br /> | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending |  | {"disabled_segments":["38f528b7-306d-4627-a2bc-775b2e01d01f-9ce5929c-3cb3-401f-abe5-7bd9e73db778","9ce5929c-3cb3-401f-abe5-7bd9e73db778-1db6aeda-5c31-4e1c-9cfe-45376970805f","1db6aeda-5c31-4e1c-9cfe-45376970805f-48f0b92e-bd96-4ae6-bc13-6a94ecc754c5","b5bfbef5-356c-499b-ad2b-351b7ed6a845-38f528b7-306d-4627-a2bc-775b2e01d01f","48f0b92e-bd96-4ae6-bc13-6a94ecc754c5-b5bfbef5-356c-499b-ad2b-351b7ed6a845"]} | true | 2025-08-11 | 2025-12-07 14:48
5e1f65a5-4809-47ba-ad2d-c5167fccb190 | HNV-24 | 2 | <strong class="text-blue-600">OFC STATUS:</strong> READY WITH EXISTING FIBER<br /> <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> | 2970fab5-24ed-47d3-b0c1-42aca2d11c79 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Partial Ready | Pending | true | {} | true | 2025-11-29 | 2025-12-07 14:48
3ae24684-ea2c-4660-8528-559e06a01e01 | HNV-25 | 4 | <strong class="text-red-600">SPEC STATUS:</strong> NOT ISSUED<br /> <strong class="text-blue-600">OFC STATUS:</strong> READY<br /> | 2970fab5-24ed-47d3-b0c1-42aca2d11c79 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Ready | Pending | true | {"disabled_segments":["dea39efc-21b8-4bf1-9254-f53c958b6378-b5bfbef5-356c-499b-ad2b-351b7ed6a845"]} | true | 2025-11-29 | 2025-12-07 14:48
b1e5c1f2-2463-4dc9-99c2-6117dfec12b1 | linear_bts | 0 |  | 2970fab5-24ed-47d3-b0c1-42aca2d11c79 | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
104775fe-4c27-44d9-a14b-0c38e21a5786 | MAAN-06 | 4 |  | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 30be8eeb-ec4f-4ce2-9935-b249e70caaec | Pending | Pending | Pending |  |  | true | 2025-10-17 | 2025-12-07 14:48
084a1289-b640-4900-9783-d05e55306fb5 | MAAN-17 | 7 |  | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 30be8eeb-ec4f-4ce2-9935-b249e70caaec | Pending | Pending | Pending |  |  | true | 2025-10-17 | 2025-12-07 14:48
0e8bf0bb-64d7-42f5-87cd-d754e6bdab27 | MAAN-19 | 0 |  | 18429ead-ad6a-46aa-8155-2b418cb5def5 | a41dc1c4-3421-48dd-a123-8c1ddd56b8ba | Pending | Pending | Pending |  |  | true | 2025-10-17 | 2025-12-07 14:48
f16f583e-5167-4c39-9436-80555517c187 | MAAN-20 | 6 |  | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 30be8eeb-ec4f-4ce2-9935-b249e70caaec | Pending | Pending | Pending |  |  | true | 2025-10-17 | 2025-12-07 14:48
c920722b-07b8-4003-984e-2b9988cc601b | MAAN-21 | 0 |  | 18429ead-ad6a-46aa-8155-2b418cb5def5 | 30be8eeb-ec4f-4ce2-9935-b249e70caaec | Pending | Pending | Pending |  |  | true | 2025-10-17 | 2025-12-07 14:48
4965a3d2-d4f7-4ae5-85e6-3211fe024ebf | MNGPAN | 0 |  | cc3cebe7-5419-4806-8d3a-6405cf00ecbb | 4bc2a086-b131-47e1-9c20-f10650c0196d | Pending | Pending | Pending |  |  | true | 2025-08-11 | 2025-12-07 14:48
fe485021-8891-4bbf-9735-b6db287c831f | VIA_HNV_CPAN | 5 | <strong class="text-green-600">OFC STATUS:</strong> Co-Located, Via Radio Link<br /> <strong class="text-green-600">SPEC STATUS:</strong> ISSUED Vide: TP/Inst. Prg/02_25/20_Revised DATED: 06-03-2025<br /> <strong class="text-green-600">BTS STATU:</strong> On Air<br /> <strong class="text-amber-600">Included Sites:</strong> Ghospara Darir Road, Mollikpur Sitala Mandir, Narendrapur-III, Sonarpur South, Subhasgram, Subhasgram Panchghara, Subhashgram Petua<br /> | 0dfc3ef0-d661-458a-b0b7-2b8b0975b6dd | 4bc2a086-b131-47e1-9c20-f10650c0196d | On-Air | Ready | Issued |  | {"disabled_segments":["53797415-2c34-4f84-a415-404932486c96-c38d739c-c0b8-40ed-b18f-b58a59647962"]} | true | 2025-08-11 | 2025-12-07 14:48